## Slide 1: Experiences from a Quality Improvement Effort Kayla Steltz & Rodrigo Franco-Laura June 13th 2024

## Slide 2: Background
Colon cancer screening age now starts at age 45.
Patients are being diagnosed younger and younger with colon cancer.
Colon cancer screening rates are low at the clinic.
Colonoscopy can take 6+ months to schedule and complete
Previous attempts have been made to increase our colon cancer screening rates

## Slide 3: Project Aim
The aim of this quality improvement was to increase the return rates of colon cancer screening kits in the Yakima Neighborhood Health patient population through video education at patient visits

## Slide 4: Fishbone Diagram
Factors considered
  Socioeconomic, visit time, patient follow up, lack of insurance, health literacy
  Resourses: MAs, computers in exam rooms, IT
We focused on changes that we can make in the clinic setting and how we could utilize time during visits

## Slide 5: Stakeholders
Quality improvement team
  Previous interventions to increase patient colon cancer screening
  Data interpretation
IT
MA
Patients

## Slide 6: Approach to Change
PDSA cycle
Met with key stakeholders within the organization
Create educational presentation for patients
Implement video education during patient visits
Two provider at the main clinic for almost 3 months
Compare rates of completed screening prior to implementation and following implementation
Determine if there is significant change and possibly implement at other sites within the organization

## Slide 7: Process
Presentations were created to inform patients on the importance of screening and how to screen.
Once a patient is identified as due for colon cancer screening, the MA will start the two-minute video at the end of the intake process.
Patients will then could ask questions when the provider enters.

## Slide 8: Data
At the start of the project, we had a return rate of 13%
After implementing we had a return rate of 27%
Limitations

## Slide 9: Results
Increase in colon cancer screening return rates among the two participating providers
  Changes in MA, patients lost to follow up, patients not completing test
We learned that all time during visits is valuable to educate patients

## Slide 10: Conclusions/Implications
The QI team plans to run a return rate per provider and per clinic to see if this would be valuable to implement elsewhere
Possibly continue this work through future residents?