## Slide 1
Quality Improvement Seminar
Mark Splaine & Emma Warshauer
February 27, 2025
Nurse Practitioner & Physician Assistant
Training Programs
INTERACTIVE
INFORMATIVE
SKILL BUILDING
TEAM WORK
STRATEGIC
FOCUSED
FUN
RELEVANT

## Slide 2: Session Goals
Review strategies for planning a Plan-Do-Study-Act (PDSA) cycle
Share examples of PDSA approaches from your projects
Hear an example from a leader regarding work with stakeholders
Review tools for communication plans and stakeholder analysis
Practice developing a stakeholder analysis plan
2

## Slide 3: Roles
Theory burst presenter
  Mark
Timekeeper & technical genius
  Emma
Take-home thoughts
  Mark and Emma
3

## Slide 4: Agenda
Welcome (5 minutes)
Another data display example (7 minutes)
PDSA case discussion (8 minutes)
A PDSA example (10 minutes)
Stakeholder examples (10 minutes)
Theory burst (10 minutes)
  Stakeholder Analysis/Influencing Strategy/Communication Plan
Summary and take-home points (5 minutes)
Break (5 minutes)
Project team work (15-30 minutes minutes)
4

## Slide 5
  An overview of Quality Improvement (10/10/24)
  Care Observations & Stakeholder Considerations (10/24/24)
  Organizing your Improvement Project (11/14/24)
  Global Aim and Fishbone Diagram (12/12/24)
  Process Mapping (Flowcharts) (1/9/25)
  Measurement to Inform Change (1/23/25 & 1/30/25)
  An Approach to Testing a Change (2/13/25)
  Communication about your Improvement Effort (2/27/25)
  Stakeholder Analysis & Conflict Management (3/13/25)
  Managing Up and Gaining Leadership Buy-In (3/27/25)
  Negotiation (4/10/25)
  Negotiation and More About Cycles of Change (4/24/25)
  Sustaining your Improvement Effort (5/8/25)
  Resident Presentations (5/22/25, 6/12/25, 6/26/25)
Curriculum Plan

## Slide 6: Another Data Display Example
6

## Slide 8
  Change 1 – initial query of patients
  Change 2 – develop scripting for MA’s
  Change 3 – provider education about vaccine risks and benefits
  Change 4 – educate staff

## Slide 9: PDSA Case Study
Any questions or issues about the case?
9

## Slide 10
PDSA Example (2023)

## Slide 11: Using a Flowchart to Show PDSA
Provider
Visit
Refer to RD
RD
Visit
Follow-up
Provider
Visit
Person w Diabetes
Outcome

## Slide 12: Possible Additional PDSA’s
Provider
Visit
Refer to RD
RD
Visit
Provider & RD
Confer
Follow-up
Provider
& RD Visit
Additional
RD Visit(s)
Follow-up
Provider Visit
Person w Diabetes
Provider & RD
Confer
Outcome

## Slide 13
Stakeholder Example: Garrett Matlick

## Slide 14: Garrett’s DNP Project
Goal was to get patients into the clinic faster after hospital discharge since, at the time, our time to intake for therapy was about 6-8 weeks, which meant that by the time they were able to get 1-2 sessions in, it might be 2-3 months before they got into psych med management.
One idea was to establish a workflow of a new therapy group where the therapist would do an intake to determine fit for group and then would do an 8 week, weekly group.
The group would focus on utilizing resources and how to avoid going back to the ED and when they should go back to the ED.
At the same time, they’d see either a primary care provider who was comfortable with psych or a psychiatry provider who would see them 1-2 times as a consult and provide feedback to the PCP on recommendations for meds, med changes, etc.
14
Notes: www.clinicalmicrosystem.org
14

## Slide 15: Garrett’s DNP Project
In order to make this happen, it required
  Having meetings with the Chief BH Officer, the On-Site BH Director for Stamford
  Surveying the therapists to see who would be interested
  Surveying psychiatry providers and PCPs to see who would be interested/have availability in their schedule
  Then working with the two individuals to come up with a plan.
It involved a lot of meetings to put into place.
The key component for these conversations though wasn’t the logistics, it was getting buy in from key stakeholders at the organization.
15
Notes: www.clinicalmicrosystem.org
15

## Slide 16: Garrett’s DNP Project
Finding a way to deliver your message in a way that shows the importance of the change and that you’ve thought through how it might work and that you have interested parties will make a big difference.
You also need to find ways to show that it will improve workflows and not simply add to responsibilities and slow things down.
And once you have buy in, you also get the added benefit of multiple minds adding their input!
16
Notes: www.clinicalmicrosystem.org
16

## Slide 17
Additional thoughts on stakeholders

## Slide 18: Stakeholder Analysis
How to use this tool
Plot where individuals currently are with regard to change (C = current)
Plot where individuals need to be (D = desired) in order to successfully accomplish change. Identify gaps between current and desired with horizontal arrows.
Indicate which individuals may influence others by drawing arrows between them.
Action steps for closing gaps will be discussed in the “Influencing Strategy.”
Stakeholder | Strongly against | Moderately against | Neutral | Moderately supportive | Strongly supportive
Providers |  |  |  | C | D
IT | C |  |  | D | 
HR |  |  | C D |  | 
Nursing |  |  |  |  | 
Reception |  |  |  |  | 
Other stakeholder |  |  |  |  | 
Not all stakeholders need to be “strongly supportive” for successful change
Notes: Understand where your stakeholders currently stand on their understanding and support of your project and test of change

## Slide 19: Stakeholder Analysis Example
Stakeholder | Strongly against | Moderately against | Neutral | Moderately supportive | Strongly supportive
Providers |  | C |  | D | 
PSAs |  |  |  | C | D
Patients |  |  | C |  | 
Nursing |  |  |  | C | D
Medical Assistants |  |  | C |  | D
Finance |  |  |  | CD | 
IT |  |  |  | CD | 
Jane Smith |  |  | C |  | 
Dental |  | C |  |  | D
Behavioral Health |  | C |  |  | D
Senior Leadership |  |  |  | C | D
Trainers/HR |  |  | C |  | 
Current State = C
Desired State = D
Notes: Example

## Slide 20: Prioritization Matrix
Notes: Organize your stakeholders into categories to help you prioritize which stakeholders need more or less communications and how much information.

## Slide 21: Communication Plan
Audience | Communication Objectives | Message(s) | Media & Methods | Timing & Frequency | Who/When Where
Media Method Examples to Consider:
Email.
Newsletter.
Teleconference.
Notice boards.
CEO briefing.
Posters.
Lunchtime meeting.
Intranet article.
Launch event.
Team meeting.
Notes: Understand the best way to communicate with your stakeholders

## Slide 22: What haven’t we figured out yet?
Questions or issues that remain unclear?
22

## Slide 23: Change Can Be Hard
23
Chip Heath, Switch: How to Change Things When Change Is Hard
“The status quo feels comfortable and steady because much of the choice has been squeezed out. You have your routines, your ways of doing things.”

## Slide 24: Summary
Many people approaching an improvement effort underappreciate the importance of the Plan step of the PDSA cycle.
The fishbone diagram can be a helpful tool for brainstorming ideas for possible changes to test. Once generated, you can prioritize the list of change ideas and begin testing those of highest priority.
Input from stakeholders is critical throughout any improvement effort. It is particularly informative when selecting an effort, developing an understanding of a process, and considering what change to test.
Because stakeholder input is important throughout an improvement effort, it is useful to have a strategy for communicating with stakeholders.
24

## Slide 25: Session X Assignment
Interview a stakeholder for your planned change with whom you have not had regular interaction regarding the change
Use the template we used today to guide your interview (see separate Word document)
Contact Mark or Emma if you have questions
Be prepared to discuss your interview next session on 3/13/25
25
Notes: www.clinicalmicrosystem.org
25

## Slide 26: Break!
Take five minutes to recharge and refresh.
26

## Slide 27: Small Group Discussion
We will use Zoom Breakout Rooms to allow you to gather as a project team
You will discuss the questions on the following slide related to a stakeholder for your project (also see the Word document template)
Answer as many of the questions as you are able
  Have one member of your team record the answers
27
Notes: www.clinicalmicrosystem.org
27

## Slide 28: Stakeholder Considerations
28
What is their level of interest in the project and/or test?
What is their level of influence on the project and/or test?
How do they want to contribute and be involved in the project?
What are their expectations for this project or test of change?
What challenges do you predict might come up regarding this stakeholder?

## Slide 29: References
HRSA.org - Health Resources and Services Administration, agency of U.S. Department of Health and Human Services, Rockville, Maryland: Testing for Improvement
Warrick DD. Developing Organization Change Champions: A High Payoff Investment! OD Practitioner. 2009;41(1):14-19.
29
Notes: www.clinicalmicrosystem.org
29