## Slide 1
Quality Improvement Seminar
Mark Splaine & Emma Warshauer
November 13, 2025
Nurse Practitioner & Physician Assistant
Training Programs
INTERACTIVE
INFORMATIVE
SKILL BUILDING
TEAM WORK
STRATEGIC
FOCUSED
FUN
RELEVANT
Notes: EMMA

## Slide 2: Session Goals
Review common health center QI infrastructure
Hear about and discuss your efforts to draft a project charter for your project idea
Consider which stakeholders may be relevant for your project
Introduce two new templates (global aim & fishbone diagram)
2
Notes: EMMA

## Slide 3: Roles
Theory burst presenter
  Mark
Facilitator, timekeeper & technical genius
  Emma
Take-home thoughts
  Emma & Mark
3
Notes: EMMA

## Slide 4: Agenda
Welcome and reminders (5 minutes)
Improvement priority examples (5 minutes)
Brief review of project charters (10 minutes)
Project charter examples (20 minutes)
Break (5 minutes)
Stakeholder considerations (20 minutes)
Summary and take-home points (5 mins)
Introduce new templates (10 minutes)
  Global aim statement
  Fishbone diagram
Preview of next session (5 minutes)
4
Notes: EMMA

## Slide 5
  An overview of Quality Improvement (10/9/25)
  Care Observations & Stakeholder Considerations (10/23/25)
  Organizing your Improvement Project (11/13/25)
  Global Aim and Fishbone Diagram (12/11/25)
  Process Mapping (Flowcharts) (1/8/26)
  Measurement to Inform Change (1/22/26 & 1/29/26)
  An Approach to Testing a Change (2/12/26)
  Communication about your Improvement Effort (2/26/26)
  Stakeholder Analysis & Conflict Management (3/12/26)
  Managing Up and Gaining Leadership Buy-In (3/26/26)
  Negotiation (4/9/26)
  Negotiation and More About Cycles of Change (4/23/26)
  Sustaining your Improvement Effort (5/14/26)
  Resident Presentations (5/28/26, 6/11/26, 6/25/26)
Curriculum Plan
Notes: EMMA

## Slide 6: Quick Reminder
At this point you should have decided on your project team
  Which residents you will work with
Also, you should have an idea about the project on which your team will focus
  Totally fine if you are still refining your idea
  We can help you, just let us know
6
Notes: EMMA

## Slide 7: Organizational QI Priorities
Where do they come from?
  Input from many levels of organization
How often are they set?
  Annually
How are they tracked?
  Multiple approaches
7
Notes: MARK

## Slide 8: Common QI Infrastructure
A Chief Quality Officer (organizational QI leader) leads a committee, organizes recommendations, and compiles a report to the senior leadership and board for approval annually
A corporate quality committee consisting of representatives from local sites, organization quality leaders, and service line/senior leaders
Board member input and involvement
  Overall Board of Directors
  Also, often a subcommittee (e.g., Compliance/Performance Improvement (CPI) committee)
Quality teams at the local clinical sites that provide initiatives for their local patient populations.
8
Notes: MARK

## Slide 9: Planning a QI Project Using a Project Charter
9
Notes: MARK

## Slide 10
Notes: MARK

## Slide 11
A PROJECT CHARTER adds structure as you plan
What are we trying to accomplish? & Why?
Will we know if the change made an impact?
  A tool for training and/or communication
  Baseline data
  Goals
  Measures
  Stakeholders
  Barriers
  Expectations
  Ideas
11
Notes: MARK

## Slide 12
Problem Statement
Create this statement with team
Team Members
Central Question/ Why work on this now?
Include each member (core and extended)
Measures
What is the impact anticipated OR what are the current losses
Scope
Goal Statement
Measurement from Performance Improvement (PI) Goals
Milestones/ Dates
Goals from team or organization’s specific statement.
Date team first meeting and date project charter created
Document first & last process steps.
Deliverables and when they are due
If implementation goal –evidence that it is implemented?
List areas of exclusion for this project
Create this statement with team
Date each PDSA launched, completed.
Project Charter Template
Date charter revised
Notes: MARK

## Slide 13
Problem Statement
Lack of consistent process for urgent BH referral (WHOs) that impacts time to care
Team Members
Central Question/ Why work on this now?
Planning team (us), data collection (medical providers, BH providers, PSAs, office manager)
Measures
Increase in need of BH services
Scope
Goal Statement
How many appointments get scheduled in a certain amount of time – (% within 48 hours)
Milestones/ Dates
Define the process related to urgent WHO so that we can decrease time to completion of WHO appointment
Middletown CHC WHO Referral Process – starting January 2022
Pandemic has exacerbated inconsistencies in process and disrupted communication between providers
Standardized interview questions to determine understanding of WHO Referral process between key stakeholders (PSA, Medical Providers, Behavioral Health Providers)
Project Charter Template Meeting – 2/22
Interviews (PSA, Medical, Behavioral) – 2/22
First Team Meeting – 11/21
Analysis of WHO process, define workflow – 3/22
Review Sharepoint WHO data – 4/22
Starting at medical referral and ending with WHO appointment scheduled
Project Charter Example
Notes: MARK

## Slide 14
Problem Statement
The texting bin to remind patients to be seen is not an effective way to increase visits
Team Members
Central Question/ Why work on this now?
Nindi Tiemo and Rebekah Mabrey
Measures
Scope
Goal Statement
Milestones/ Dates
The goal of this project is to prove the efficacy of the texting bin in its goal of getting patients to follow-up with their provider.
The texting bin is supposed to help remind patients to schedule appointments with their providers in order to have adequate follow-up care. However, provider perception is that they either do not bother using it and/or it does not do an adequate job reaching patients. Potential barriers are messages being sent in English and being sent to phones that may not be able to receive messages or receive messages at any time.
Early Version of 2nd Example
Notes: MARK

## Slide 15
Problem Statement
The texting bin is not an effective tool to schedule appointments
Team Members
Central Question/ Why work on this now?
Nindi Tiemo and Rebekah Mabrey
Measures
Scope
Goal Statement
Languages offered for text messages? Will patient phone plans allow for messages to go through? What exactly do the messages say (what kind of information is given to patients)?
Milestones/ Dates
The goal of this project is to prove the efficacy of the texting bin in its goal of getting patients to follow-up with their provider
Team meeting to initiate project
First step: Choose project topic – Discuss with different providers ideas they may have for QI projects
The texting bin is supposed to help remind patients to schedule appointments with their providers in order to have adequate follow-up care. However, provider perception is that they either do not bother using it and/or it does not do an adequate job reaching patients. Potential barriers are messages being sent in English and being sent to phones that may not be able to receive messages or receive messages at any time.
Last step: Provide education to providers regarding how to utilize the texting bin and the data we have acquired showing the efficacy of the tool
Meeting with Alexis to learn more about texting bin
A Second Example
Notes: MARK

## Slide 16
  Does any team want to share a brief summary of their charter?
  Was there anything you found challenging or got stuck on in drafting the charter?
Group Discussion
Notes: MARK

## Slide 17: Break!
Take five minutes to recharge and refresh.
17
Notes: MARK

## Slide 18: Poll Question
How do you feel about using the project charter to inform the development of your project as it moves forward? (select one)
  Really good; we are on track with a solid plan.
  Good; making progress, and we still have some issues to consider.
  So so; we are getting there and would benefit from some assistance.
  Not so good; we are struggling a bit and could use some guidance.
18
Notes: EMMA

## Slide 19
  Stakeholders are anyone who may be impacted by your project, or whose assistance/guidance you may need for carrying out your project.
  Common stakeholders team’s have consulted with include:
    Organization or site leaders
    Other members of your clinical team
    Patient/clients
  There may be others to consider based on the topic of your project
Stakeholder Considerations
Notes: EMMA

## Slide 20
  We will divide into two breakout groups
  Emma will facilitate one group, Mark the other
  In your group, share about the following:
    What is your project topic?
    Who are some stakeholders you are thinking you may need to get in touch with?
Stakeholder Discussion
Notes: EMMA

## Slide 21: Discussion Groups
Emma’s Group
Montefiore Medical Group
Sun River Health
Yakima NHS
CHC Meriden
CHC New London
CHC Middletown
Mark’s Group
DePaul CHC
UC Irvine
Holyoke HC
Open Door
CHC Hartford
CHC New Britain
21
Notes: www.clinicalmicrosystem.org
21
EMMA

## Slide 22: What haven’t we figured out yet?
Questions or issues that remain unclear?
22
Notes: MARK

## Slide 23: Take-home Thoughts
Emma & Mark – share 1 or 2 ideas you will take away from our small group discussion
23
Notes: MARK & EMMA

## Slide 24: Summary
You have learned about a framework to guide your thinking about how to organize improvement work
Also, we have reviewed an important tool for quality improvement work – the project charter
Based on our discussion, it is clear you are already making good initial progress on your projects.
Our next step will be setting a clear goal and understanding a problem you are wanting to address in your project work.
24
Notes: MARK

## Slide 25: Additional Templates
Global Aim & Fishbone
25
Notes: MARK

## Slide 26: Writing a Structured Global Aim:
The aim is to improve the quality and value of... (name the process)
The process starts with... (name start point) and the process ends when… (name end point) .
By working on this we expect to:
  (Name better, hoped for results)
It is important to work on this now because…. (list reasons) .
Notes: MARK

## Slide 27
Fishbone (Cause & Effect) Diagram
A team works together with a structured approach to brainstorming a list of causes of a problem
The head of the fish is the problem: Late for work.
The bones are causes grouped by category.
Notes: EMMA

## Slide 28: Using the Fishbone Template
The Head of the fish = The Problem (or effect): Team must agree on the problem statement in the global aim first!
What general categories will you use? Typical ones include:
  Equipment/supplies
  Technology
  Staff
  Processes/procedure
  Environment
  Patients
Each bone = Contributing Causes within a category
Focus on current state!! No solutions yet!
Don’t worry about messiness
Notes: EMMA

## Slide 29: Session IV Highlights
We will hear reports from several groups about their draft global aim statement for their project idea
We will work in breakout groups to brainstorm causes for a problem statement using the fishbone diagram template
29
Notes: www.clinicalmicrosystem.org
29
EMMA

## Slide 30: Assignment for Session IV
If you are not familiar with the idea of brainstorming, watch the two brief videos for examples of a group brainstorming
Session preparation (review the templates):
  Global aim statement
  Fishbone (cause-and-effect) diagram
Work with your project team to generate a draft of a global aim statement for your project topic
Contact Mark or Emma if you have questions or need assistance
Send your draft global aim to Mark and Emma by Wednesday (12/10/25) at 6pm EST
Our next session will be on Thursday, 12/11/25
30
Notes: www.clinicalmicrosystem.org
30
EMMA

## Slide 31: Videos to Review
The two video links provided below will give you a brief introduction to how a group does brainstorming
  https://www.youtube.com/watch?v=9K8W4ooygUU (overview, roughly 4 minutes)
  https://vimeo.com/9849184 (example, roughly 2 minutes)
31
Notes: www.clinicalmicrosystem.org
31
EMMA

## Slide 32: Upcoming Office Hours & Teams
The next office hours will be on 11/20 from 11:30am-12:30pm EST
We would like to meet with each project team once during November, December, or January. Please let us know when your team would like to do this (in office hours or at another time).
This discussion will be for us to learn a bit more about your project plan and to think together how we can assist you in your work
32
Notes: www.clinicalmicrosystem.org
32
EMMA

## Slide 33: References
Splaine ME, Dolansky MA, Estrada CA, and Patrician PA. Practice-Based Learning and Improvement: A Clinical Improvement Action Guide (3rd Edition). Oakbrook Terrace, IL: Joint Commission Resources, 2012.
Langley GJ, Moen R, Nolan KM, Nolan, TW, Norman CL, and Provost LP. The Improvement Guide: A Practical Approach to Enhancing Organizational Performance (2nd Edition). San Francisco, CA: Jossey-Bass, 2009.
33
Notes: www.clinicalmicrosystem.org
33
EMMA

## Slide 34: We wish you all a wonderful and safe holiday!
34
Notes: MARK